## Project Plan - Updated
| DETAILED PROJECT PLAN | PROJECT NAME | ISO 27001: 2022 TRANSITION ISO 27017:2015 ISO 22301:2019 ISO 27701:2019 IMPLEMENTATION, COMPLAINCE & RECERTIFICATION PROJECT
|  | CLIENT NAME | Client Name | [5 empty] | Overall Completion | #DIV/0! |  | 99.09%
|  | ESTIMATED PROJECT DURATION | 5 WEEKS
| Task Name | Deliverables | Depenedency | Week | Task Ownership | Comments | Completed | Status
1 | ISO Foundation
1.1 | Detailed Project Plan | [8 empty] | Overall Completion
1.1.1 | Kickoff Meeting | Project Plan |  | Week 01 | Secureitlab |  | 100% | COMPLETED
1.1.2 | Information request ( existing documentation, policies, and procedures, if any) |  |  | Week 01 | Client Name |  | 100% | COMPLETED
1.1.3 | Develop and submit project plan |  |  | Week 01 | Secureitlab |  | 100% | COMPLETED |  | Status | Count of Status
1.1.4 | Project Plan Approval |  |  | Week 01 | Client Name |  | 100% | COMPLETED |  | COMPLETED | 14
[10 empty] | IN PROGRESS | 4
1.2 | ISMS and PIMS Scope | [8 empty] | TO BE STARTED | 54
1.2.1 | Meeting with the POC for - Understanding the context of the organization - Define the purpose and objectives of the BCMS scope - Identify the boundaries of the BCMS - Identify internal & external dependencies - List the assets and resources covered by the BCMS - Review the current scope document of ISMS and update it according to ISO 27001:2022 version. - Extend the scope to include cloud services. PIMS and Cloud - Identify the boundaries of Privacy Information Management System (PIMS) and Cloud - Identify and Establish Roles and Responsibilities | Scope Document |  | Week 01 | Client Name - Secureitlab |  | 100% | COMPLETED | Overall Completion | #DIV/0! | 88.05%
1.2.2 | Develop the formal scope document |  | 1.2.1 | Week 01 | Secureitlab |  | 100% | COMPLETED
1.2.3 | Submit draft for review |  | 1.2.1 | Week 01 | Secureitlab |  | 100% | COMPLETED
1.2.4 | Incorparate any changes of the review |  | 1.2.1 | Week 01 | Secureitlab |  | 100% | COMPLETED
1.2.5 | Submit the final scope documents |  | 1.2.4 | Week 01 | Client Name - Secureitlab |  | 100% | COMPLETED
1.3 | Establishing Top mangement commitment for the ISMS & BCMS
1.3.1 | Identify if existing Steering committee operational for Information Security and Business Continuity | Review of Steering committee |  | Week 01 | Secureitlab |  | 100% | COMPLETED
1.3.2 | Meeting with POC to understand and assess existing top management commitment toward the ISMS & BCMS (if any) - Members, their designation and roles & responsibilities - Meeting frequency - Discussion points - Action plan |  |  | Week 01 | Client Name - Secureitlab |  | 100% | COMPLETED
1.3.3 | Formalize the existing practice to meet the ISMS & BCMS requirements |  | 1.3.2 | Week 01 | Secureitlab |  | 100% | COMPLETED
1.4 | Gap Analysis
1.4.1 | Gather and review the existing documentation, current assessment results, previous Internal Audit findings and Risk Assessment results. | Gap Analysis Report | 1.1.2 | Week 01 | Secureitlab |  | 100% | COMPLETED
1.4.2 | ISO 27001 Transition: Review the requirements from new controls of ISO 27001:2022 in order to identify current gaps |  |  | Week 01 | Secureitlab |  | 100% | COMPLETED
1.4.3 | Meeting with POC to understand controls implementation for existing and the following new controls as per ISO 27001:2022: A.5.7 Threat intelligence A.5.23 Information security for use of cloud services A.5.30 ICT readiness for business continuity A.7.4 Physical security monitoring A.8.9 Configuration management A.8.10 Information deletion A.8.11 Data masking A.8.12 Data leakage prevention A.8.16 Monitoring activities A.8.23 Web filtering A.8.28 Secure coding |  |  | Week 01 | Client Name - Secureitlab |  | 100% | COMPLETED
1.4.4 | Meeting with POC to understand controls implementation, ISO 27017:2015, ISO 22301:2019 and ISO 27701:2019 |  |  | Week 01 | Client Name - Secureitlab |  | 100% | COMPLETED
1.4.5 | Collect evidences for new and existing controls based upon discussion with POC. |  | 1.4.3, 1.4.4 | Week 01 | Secureitlab |  | 100% | COMPLETED
1.4.6 | Review and analyze the gathered evidences |  |  | Week 01 | Secureitlab |  | 100% | COMPLETED
1.4.7 | Submit the draft gap analysis report |  |  | Week 01 | Client Name - Secureitlab |  | 100% | COMPLETED
1.4.8 | Update the report based on the meeting with POC. |  |  | Week 01 | Secureitlab |  | 100% | COMPLETED
1.5 | Controls Implementation Roadmap
1.5.1 | Develop a detailed transition roadmap outlining specific tasks, responsible parties, timelines, and resources required for ISO 27001:2022 control implementation. | Control Implementation Roadmap |  | Week 01 | Secureitlab |  | 100% | COMPLETED
1.5.2 | Develop a detailed implementation roadmap outlining specific tasks, responsible parties, timelines, and resources required for ISO 27017:2015, ISO 22301:2019 and ISO 27701:2019 control implementation. |  |  | Week 01 | Secureitlab |  | 100% | COMPLETED
1.5.3 | Share with POC for feedback |  |  | Week 01 | Secureitlab |  | 100% | COMPLETED
1.5.4 | Update the implementation roadmap for feedback |  | 1.5.2 | Week 01 | Client Name - Secureitlab |  | 100% | COMPLETED
1.5.5 | Submit finalized implementation road map |  |  | Week 01 | Secureitlab |  | 100% | COMPLETED
2 | Risk Assessment
2.1 | Risk management Framework as per ISO 27005:2022
2.1.1 | Review the existing framework and develop the Risk Management methodology based on risk assessment ISO standard 27005:2022 | Risk Management framework Risk Management Methodology |  | Week 01 | Secureitlab |  | 100% | COMPLETED
2.1.1 | Identify Risk scenarios, Threats & Vulenrabiliites pertaining to Client Name as per ISO 27005:2022 |  |  | Week 01 | Secureitlab |  | 100% | COMPLETED
2.1.3 | Develop risk management methodology |  |  | Week 01 | Secureitlab |  | 100% | COMPLETED
2.1.4 | Develop the risk management framework inline with ISO 27005:2022 requirements |  |  | Week 01 | Secureitlab |  | 100% | COMPLETED
2.1.5 | Submit final risk management framework |  |  | Week 01 | Secureitlab |  | 90% | IN PROGRESS
2.2 | Information Asset Register
2.2.1 | Identify all Client Name's information assets | Information Asset Register | 1.1.2 | Week 02 | Client Name - Secureitlab |  | 100% | COMPLETED
2.3 | Asset evaluation
2.3.1 | Develop Asset classification criteria |  |  | Week 02 | Secureitlab |  | 100% | COMPLETED
2.3.2 | Present and formalise Asset classification criteria |  |  | Week 02 | Client Name - Secureitlab |  | 100% | COMPLETED
2.3.3 | Submit final information asset register |  | 2.2.1 | Week 02 | Client Name - Secureitlab |  | 100% | COMPLETED
2.4 | Business Impact Analysis
2.4.1 | Introductory presentation on Business Impact Analysis | Business Impact Analysis Report |  | Week 02 | Secureitlab |  | 100% | COMPLETED
2.4.2 | Document all key business operations and processes |  |  | Week 02 | Client Name - Secureitlab |  | 100% | COMPLETED
2.4.3 | Assess the potential impact of disruptions on revenue, customer service, compliance, and reputation. |  | 2.2.1 | Week 02 | Client Name - Secureitlab |  | 100% | COMPLETED
2.4.4 | Identify internal and external systems, applications, and third-party services that support critical business functions. |  |  | Week 02 | Secureitlab |  | 100% | COMPLETED
2.4.5 | Analyze the risk exposure and its impact on business operations. |  |  | Week 02 | Secureitlab |  | 100% | COMPLETED
2.4.6 | Determine acceptable downtime and data loss thresholds for critical processes and services. |  |  | Week 02 | Client Name - Secureitlab |  | 100% | COMPLETED
2.4.7 | Review the roles, skillsets, and resources required for recovery and continuity during and after a disruption. |  |  | Week 02 | Client Name - Secureitlab |  | 100% | COMPLETED
2.4.8 | Engage with department heads and key stakeholders to understand business priorities, processes, and recovery needs. |  |  | Week 02 | Client Name - Secureitlab |  | 100% | COMPLETED
2.4.9 | Identify potential legal or regulatory compliance issues in the event of disruptions to business activities. |  |  | Week 02 | Client Name - Secureitlab |  | 100% | COMPLETED
2.4.10 | Document the BIA results and propose risk mitigation measures, including backup systems, alternative vendors, or continuity planning improvements. |  | 2.4.3 - 2.4.9 | Week 02 | Secureitlab |  | 100% | COMPLETED
2.4.11 | Establish a process for periodically reviewing and updating the BIA based on business changes, new risks, or evolving regulations. |  |  | Week 02 | Secureitlab |  | 100% | COMPLETED
2.5 | Privacy Impact Assessment
2.5.1 | Introductory presentation on Privacy Impact Assessment | Privacy Impact Assessment Report |  | Week 02 | Secureitlab |  | 100% | COMPLETED
2.5.2 | Identify all data collected from individuals and organizations, including personal, organizational, and sensitive data. |  |  | Week 02 | Secureitlab |  | 100% | COMPLETED
2.5.3 | Determine the involvement of any third-party access and processing of the data. |  |  | Week 02 | Secureitlab |  | 100% | COMPLETED
2.5.4 | Assess data processing activities, which include data collection, processing, storage, and sharing |  |  | Week 02 | Secureitlab |  | 100% | COMPLETED
2.5.5 | Conduct Privacy risk assessment as per privacy by design principles |  |  | Week 02 | Secureitlab |  | 100% | COMPLETED
2.5.6 | Meeting with POC to understand current PII practices. |  |  | Week 02 | Secureitlab |  | 100% | COMPLETED
2.5.7 | Conduct a Privacy Risk Assessment |  |  | Week 02 | Secureitlab |  | 100% | COMPLETED
2.5.8 | Identify risks to Personally Identifiable Information (PII) stored or processed. |  |  | Week 02 | Secureitlab |  | 100% | COMPLETED
2.5.9 | Gather and review the evidences with POC of current controls |  |  | Week 02 | Client Name - Secureitlab |  | 100% | COMPLETED
2.6 | Risk Evaluation & Treatment
2.6.1 | Introductory presentation on risk evaluation | Risk Assessment / Risk Treatment Plan Risk Assessment Report |  | Week 02 | Secureitlab |  | 100% | COMPLETED
2.6.2 | Develop risk assessment questionnaire |  |  | Week 02 | Secureitlab |  | 100% | COMPLETED
2.6.3 | Evaluate inherent risks |  |  | Week 02 | Secureitlab |  | 100% | COMPLETED
2.6.4 | Gather and review the evidences with POC of current controls |  |  | Week 02 | Client Name - Secureitlab |  | 100% | COMPLETED
2.6.5 | Evaluate the likelihood and impact of identified controls over inherent risk. |  | 2.2.2 | Week 02 | Secureitlab |  | 100% | COMPLETED
2.6.6 | Calculate the risk level for each identified risk as per risk matrix |  |  | Week 02 | Secureitlab |  | 100% | COMPLETED
2.6.7 | Develop risk acceptance, treatment and residual plan |  |  |  | Secureitlab |  | 100% | COMPLETED
2.6.8 | Submit draft RA/RT report |  |  | Week 02 | Secureitlab |  | 100% | COMPLETED
2.6.9 | Submit the final privacy risk assessment report to the Client Name team |  |  | Week 02 | Client Name - Secureitlab |  | 100% | COMPLETED
2.6.10 | Update RA/RT and assessment report for any changes as per the review |  |  | Week 02 | Secureitlab |  | 100% | COMPLETED
2.6.11 | Submit final RA/RT and assessment report |  |  | Week 02 | Secureitlab |  | 100% | COMPLETED
2.7 | Steering Committee Meeting
2.7.1 | Conduct the steering committee, ensuring that the following areas are covered, but not limited to: - Overview of the detailed transition steps for implementing ISO 27001:2022 controls. - Gaps identified in existing policies, procedures, and controls related to the ISO 27017:2015, ISO 22301:2019 and ISO 27701:2019 standard. - Overview of risk management strategies and alignment with the ISO 27005 standards. - Overview of Business Impact Analysis and Privacy Impact Assessment - Project Update and Next Steps | Risk Assessment / Risk Treatment Plan Risk Assessment Report |  | Week 03 | Secureitlab |  | 50% | IN PROGRESS
3 | Documentation & Framework
3.1 | ISO Framework Development
3.1.1 | Review the existing Security policies,procedures, baselines, guidelines | New Set of Issue Specific Policies, Procedures, Baseline and Guidelines ISMS, BCMS and PIMS Manual(s) | 1.4 | Week 03 | Secureitlab |  | 100% | COMPLETED
3.1.2 | Create and share the list of new issue specifc and mandatory policies, procedures, baselines, guidelines to be developed based on ISO 27001:2022 |  |  | Week 03 | Secureitlab |  | 100% | COMPLETED
3.1.3 | Create and share the list of issue specifc and mandatory policies, procedures, baselines, guidelines to be developed / updated based on ISO 27017:2015, ISO 27018:2019 and ISO 27701:2019 |  |  | Week 03 |  |  | 100% | COMPLETED
3.1.4 | Update and Develop the specifc and mandatory policies, procedures, baselines, guidelines and the ISMS, BCMS and PIMS manuals. |  |  | Week 03 | Secureitlab |  | 100% | COMPLETED
3.1.5 | Develop and reflect the changes for new controls in policies, procedures, baselines, guideline as per ISO 27001:2022 requirement |  |  | Week 03 |  |  | 100% | COMPLETED
3.1.6 | Share draft policies, procedure, baselines, guidelines and the ISMS, BCMS and PIMS manual |  |  | Week 03 | Secureitlab |  | 100% | COMPLETED
3.1.7 | Update the policy, procedures, baselines guidelines and ISMS, BCMS and PIMS manual based on the review |  | 3.1.3 | Week 03 | Client Name - Secureitlab |  | 100% | COMPLETED
3.1.8 | Submission of final policy, procedures, guidelines and mandatory manuals |  |  | Week 03 | Secureitlab |  | 0% | TO BE STARTED
3.2 | Data Privacy Framework Development
3.2.1 | Define Data Privacy Framework requirements and scope | Data Privacy Policies and Procedures |  | Week 03 | Secureitlab |  | 100% | COMPLETED
3.2.2 | Prepare the list of required data privacy policies and procedures |  |  | Week 03 | Secureitlab |  | 100% | COMPLETED
3.2.3 | Prepare consent forms and disclosures for the handling of any personal information. |  |  | Week 03 | Secureitlab |  | 100% | COMPLETED
3.2.4 | Develop the data privacy policies and procedures in line to the regulatory requirements |  |  | Week 03 | Secureitlab |  | 100% | COMPLETED
3.2.5 | Prepare and finalize the data privacy policies based on the inputs received from the Data Privacy Office |  |  | Week 03 | Client Name - Secureitlab |  | 100% | COMPLETED
3.2.6 | Submit the final data privacy policies to the management |  |  | Week 03 | Secureitlab |  | 100% | COMPLETED
3.3 | Develop Business Continuity Plans
3.3.1 | Design Incident Response Procedures | Business Continuity Plans (BCPs) |  | Week 03 | Secureitlab |  | 100% | COMPLETED
3.3.2 | Design and Establish Crisis Management Procedures |  |  | Week 03 | Secureitlab |  | 100% | COMPLETED
3.3.3 | Create communication protocols to ensure effective internal and external communication during and after an incident or crisis. |  |  | Week 03 | Secureitlab |  | 100% | COMPLETED
3.3.4 | Create detailed Business Continuity Plans (BCPs) for each critical business process identified during the BIA. |  | 2.4 | Week 03 | Secureitlab |  | 100% | COMPLETED
3.3.5 | Align Business Continuity Plans (BCPs) with Disater Recovery Plan, Incident Response and Crisis Management Procedures. |  | 3.3.3 | Week 03 | Client Name - Secureitlab |  | 100% | COMPLETED
3.3.6 | Develop and conduct testing and simulation exercises to validate the effectiveness of incident response procedures and BCPs. |  |  | Week 03 | Client Name - Secureitlab |  | 100% | COMPLETED
3.4 | Statement of Applicability
3.4.1 | Update the Statement of Applicability as per ISO 27001:2022 | Statement of Applicability (SoA) |  | Week 03 | Secureitlab |  | 100% | COMPLETED
3.4.2 | Evaluate and update the Statement of Applicability, specifying whether each control is applicable, not applicable for ISO 27017:2015, ISO 22301:2019 and ISO 27701:2019 standard |  |  | Week 03 | Secureitlab |  | 100% | COMPLETED
3.4.3 | Share the Statement of Applicability for feedback. |  |  | Week 03 | Secureitlab |  | 100% | COMPLETED
3.5 | Develop ISMS Compliance Program
3.5.1 | Identify and propose relevant information security objectives | ISMS compliance program |  | Week 03 | Secureitlab |  | 100% | COMPLETED
3.5.2 | Develop where possible measurement and monitoring parameters for objectives |  |  | Week 03 | Secureitlab |  | 100% | COMPLETED
3.5.3 | Develop resource and responsibility matrix for the information security objectives |  |  | Week 03 | Secureitlab |  | 100% | COMPLETED
3.5.4 | Develop and finalise frequency and evaluation criteria for the information security objectives |  |  | Week 03 | Secureitlab |  | 100% | COMPLETED
3.5.5 | Submit draft Information security objectives and ISMS compliance program. |  | 3.3.3 | Week 03 | Client Name - Secureitlab |  | 100% | COMPLETED
3.5.6 | Discuss any changes if required |  |  | Week 03 | Client Name - Secureitlab |  | 50% | IN PROGRESS
3.5.7 | Submit Final Information Security objectives and ISMS compliance program. |  | 3.3.6 | Week 03 | Secureitlab |  | 50% | IN PROGRESS
3.6 | Guidance for PII Controllers and Processors
3.6.1 | Define Roles and Responsibilities of PII Controllers and Processors | PII Controllers and Processors Guidance |  | Week 04 | Secureitlab |  | 100% | COMPLETED
3.6.2 | Develop Data Processing Agreements |  |  | Week 04 | Secureitlab |  | 100% | COMPLETED
3.6.3 | Establish Data Subject Rights Management Process |  |  | Week 04 | Secureitlab |  | 100% | COMPLETED
3.7 | Establish Breach Notification Procedures & DPA
3.7.1 | Define processes for identifying and reporting data breaches involving PII. | Breach Notification Procedure & DPA |  | Week 04 | Secureitlab |  | 100% | COMPLETED
3.7.2 | Include notification timelines and responsibilities. |  |  | Week 04 | Secureitlab |  | 100% | COMPLETED
3.7.3 | Define Data Processing Agreements (DPAs) |  |  | Week 04 | Secureitlab |  | 100% | COMPLETED
3.8 | ICT readiness for Business Continuity
3.8.1 | Review the existing Business Impact Analysis and Business Continuity Plan. | Business Impact Analysis Sheet | 2.4 | Week 04 | Secureitlab |  | 100% | COMPLETED
3.8.2 | Conduct a meeting to revise the BCP Plan |  |  | Week 04 | Secureitlab |  | 100% | COMPLETED
3.8.3 | Share the BIA draft for updates to Threat Profiling, RTO, RPO & MTPoD |  |  | Week 04 | Client Name - Secureitlab |  | 100% | COMPLETED
4 | Performance evaluation
4.1 | Internal Audit
4.1.1 | Develop an internal audit plan that outlines the objectives, criteria, scope, methodology, and resources required, incorporating the new ISO 27001:2022 controls, along with PII, Business Continuity, and PIMS requirements. | Internal Audit Plan Internal Audit Report |  | Week 05 | Secureitlab |  | 50% | IN PROGRESS
4.1.2 | Discuss with the POC the details objectives, criteria, scope, methodology, and resources required. |  |  | Week 05 | Client Name - Secureitlab |  | 50% | IN PROGRESS
4.1.3 | Update the internal audit plan based on the feedback shared and schedule. |  |  | Week 05 | Secureitlab |  | 0% | TO BE STARTED
4.1.4 | Communicate with IA department to include ISMS, PII, Business Continuity and PIMS audit within the audit program |  | 4.1.3 | Week 05 | Secureitlab |  | 0% | TO BE STARTED
4.1.5 | Conduct Internal Audit as per the shared ISMS, PII, Business Continuity and PIMS audit plan |  |  | Week 05 | Secureitlab |  | 0% | TO BE STARTED
4.1.6 | Create a comprehensive audit report based on the findings, detailing the audit scope and results for corrective actions. |  |  | Week 05 | Secureitlab |  | 0% | TO BE STARTED
4.1.7 | Share the audit report with Client Name. |  |  | Week 05 | Secureitlab |  | 0% | TO BE STARTED
4.2 | Training Awareness
4.2.1 | Review the existing security awareness program for Information Security, Business Continuity, PIMS and Data Privacy | Awareness Training Material Awareness Training Sessions |  | Week 05 | Secureitlab |  | 50% | IN PROGRESS
4.2.2 | Develop plan to conduct security training workshops. |  |  | Week 05 | Secureitlab |  | 0% | TO BE STARTED
4.2.3 | Develop the training material for different audiences. |  |  | Week 05 | Secureitlab |  | 0% | TO BE STARTED
4.2.4 | Update the security Training Material based on the feedback shared. |  | 4.2.3 | Week 05 | Client Name - Secureitlab |  | 0% | TO BE STARTED
4.2.5 | Send training email to all attendees |  |  | Week 05 | Client Name - Secureitlab |  | 0% | TO BE STARTED
4.2.6 | Conduct Awareness trainings |  | 4.2.5 | Week 05 | Secureitlab |  | 0% | TO BE STARTED
4.3 | Certification Audit Support
4.3.1 | Support Client Name during the external Certification Audit Process |  |  |  | Secureitlab
4.2.2 | Track any findings or non-conformities raised by the auditors and ensure immediate action is taken to address these issues. |  |  |  | Secureitlab
COMPLETED
IN PROGRESS
TO BE STARTED

## Meeting Dates
Meeting Dates
S. NO | Date | Task number | Agenda | Proposed Time (To be Filled by Client Name) | Duration | Required / Optional | Status
1 | 2025-01-02 | 1.1.1 | KickOff Meeting |  | 30 mts | Required | TO BE STARTED
2 | TBD | 1.2.1 | Meeting with the POC for - Understanding the context of the organization - Define the purpose and objectives of the BCMS scope - Identify the boundaries of the BCMS - Identify internal & external dependencies - List the assets and resources covered by the BCMS - Review the current scope document of ISMS and update it according to ISO 27001:2022 version. - Extend the scope to include cloud services. PIMS and Cloud - Identify the boundaries of Privacy Information Management System (PIMS) and Cloud - Identify and Establish Roles and Responsibilities |  | 2 hr | Required | TO BE STARTED
3 | TBD | 1.3.2 | Meeting with POC to understand and assess existing top management commitment toward the ISMS (if any) - Members, their designation and roles & responsibilities - Meeting frequency - Discussion points - Action plan |  |  | Required | TO BE STARTED
4 | TBD | 1.4.3,1.4.4 | Meeting with POC to understand controls implementation of ISO 27001:2022, ISO 27017:2015, ISO 27018:2019 and ISO 27701:2019 |  |  | Required | TO BE STARTED
5 | TBD | 2.4.1 | Introductory presentation on Business Impact Analysis |  | 30 mts | Required | TO BE STARTED
6 | TBD | 2.5.1 | Introductory presentation on Privacy Impact Assessment |  | 30 mts | Required | TO BE STARTED
7 | TBD | 2.6.1 | Introductory presentation on risk evaluation |  | 30 mts | Required | TO BE STARTED
7 | TBD | 2.7.1 | Conduct Steering committee, ensuring that the following areas are covered, but not limited to: - Overview of the detailed transition steps for implementing ISO 27001:2022 controls. - Gaps identified in existing policies, procedures, and controls related to the ISO 27017:2015, ISO 22301:2019 and ISO 27701:2019 standard. - Overview of risk management strategies and alignment with the ISO 27005 standards. - Overview of Business Impact Analysis and Privacy Impact Assessment - Project Update and Next Steps |  | 1 Hr | Required | TO BE STARTED
8 | TBD | 3.3 | Business Continuity Plans Discussion |  | 1 Hr | Required | TO BE STARTED
9 | TBD | 3.5 | ISMS Complinace Program Discussion |  | 1 Hr | Required | TO BE STARTED
10 | TBD | 4.1 | Internal Audit |  | 3 Hr | Required | TO BE STARTED
11 | TBD | 4.2 | Training Awareness |  | 1 Hr | Required | TO BE STARTED

## Week Cell Colors (hidden)
Week 01
Week 02
Week 03
Week 04
Week 05
Week 06
Week 07
Week 08